## Sheet1
RAID Log - AI-Powered Financial Advice Chatbot MVP
Category | Description | Owner | Mitigation/Action | Priority
Risks
R01 | Data security and privacy risks due to handling sensitive financial information. | Data Team | Implement security measures, follow relevant compliance regulations. | Medium
R02 | Potential delay in deployment due to issues with cloud service integration. | DevOps Team | Collaborate with cloud provider early, conduct performance tests, and have a backup plan. | Medium
R03 | Incorrect or misleading financial advice from chatbot. | Data Team | Limit advice to basic general information, and review by financial experts. | High
R04 | Scope creep during MVP development. | Business Analyst Team | Define strict scope requirements for MVP and follow Agile framework for controlled iterations. | High
Assumptions
A01 | The chatbot will only provide basic financial advice. | Data Team | Ensure clear communication with stakeholders. | Medium
A02 | The cloud provider will ensure scalability and high availability. | DevOps Team | Choose a reliable and tested cloud service provider (AWS). | High
A03 | Data base is ready to develop | Development Team | Implemented mock databse schema as a stand in | Medium
Issues
I01 | Delay in team availability leading to slowdowns in development. | Development / Data Team | Reallocate resources or adjust timeline as necessary. | High
I02 | Integration challenges with the new chatbot with existing infrastructure. | Development Team | Ensure technical feasibility and conduct compatibility tests with existing systems. | High
Dependencies
D01 | Financial experts to verify the accuracy of financial advice given by the chatbot. | Data Team | Schedule regular reviews with the financial experts throughout the development process. | Medium
D02 | Timely access to cloud infrastructure for testing and deployment. | DevOps Team | Set up cloud environment early in the project. | High
D03 | Compliance approval from the legal and regulatory team. | Data Team | Start compliance reviews in parallel with development to avoid delays. | High
D04 | GPT-4 API approval | Development Team | Prioritising other areas of the application | Medium
D05 | Testing can only be done with a deployed product | Testing Team | Making sure all backend is tested thoroughly as possible - communication and collaboration. | Medium