Scope
1. Introduction
Project Name: Chatbot for a finance company
2. Project Overview
The company want a MVP (Minimum Viable Project) of an AI powered chatbot so that it reduces workload and enhances customer service.

3. Project Objectives
- Develop a basic chatbot capable of handling common customer inquiries.
- Provide basic financial advice functionalities.
- Reduced workload for employees in the company.
- Enhanced customer service with the chatbot’s help.
- Deploy the chatbot on a cloud service provider for reliability and scalability.
- Customer’s data security and privacy compliance.
4. Deliverables
- Detailed project plan and requirements document.
- Chatbot conversation flow and integration design.
- Integration with simple financial databases and APIs for real-time information.
- Cloud service that successfully stores the chats and is used to improve the customers’ chatbot experience.
- Developed and tested AI-powered financial chatbot (MVP).
- Deployment and CI/CD pipelines.
- Basic user documentation and training materials.
- Final project report and closure document.

5. Project Constraints
- Timeline: 2 weeks
- Must ensure data security and privacy compliance
- Lack of testing process experience?

6. Out of Scope
- Advanced financial advisory services.
- Integration with complex third-party systems.
- Development of a mobile application.

7. Key Stakeholders
- Tommy Mitchell
- Clients on site (tbc)
8. Milestones
- Initiation and planning (24/09-25/09): project kick off meeting, requirement gathering, project scope design, project plan development, distribution of responsibilities, API tools analysis.
- Design (26/09- 27/09):
- Development (27/09-01/10):
- Testing (02/10):
- Deployment and go-live (03/10):
9. Assumptions
Client wants to know about our skills.

10. Risks
There will be people leaving and new people joining the team

Data Security and Privacy Risks (Confidentiality Breaches, failure to adhere to financial industry regulations, Data leakage (API increases the risk of unauthorized data access)
Mitigation:
- Implement strong encryption for data in transit and at rest.
- Establish user authentication and authorization protocols.
- Regularly conduct security audits and intrusion testing.

Accuracy and reliability risks (inaccurate financial advice, outdated information)
Mitigation:
- Implement rigorous testing and validation processes for the chatbot's responses.
- Establish a system for regular updates of financial information and APIs.
- Include clear disclaimers about the limitations of automated financial advice.

User Adoption and Training Risks (Users might misinterpret or misuse the chatbot's capabilities, leading to dissatisfaction)
Mitigation:
- Develop comprehensive, user-friendly training materials and documentation.
- Implement a feedback mechanism to continuously improve the chatbot based on user experiences.

Technical and Operational Risks (Downtime, Scalability Issues… the chosen cloud service may not adequately handle increased user load)
Mitigation:
- Choose a cloud provider with robust scalability options and implement load balancing.
- Establish a reliable backup and disaster recovery plan.

Regulatory Risks (Changing regulations/laws… requires frequent updates, cross-border compliance… If accessible internationally, the chatbot may need to comply with various regional financial regulations)

Mitigation:
- Establish a process for regular regulatory reviews and updates.
- Implement geofencing or region-specific versions of the chatbot if necessary.

-Roles
BA- Tan, Sabah & Miranda
DevOps Engineer- James
Developers - Lewis, Kian, Chris, Ollie & Jai
Data Engineer- Luis & Yoonhee
Software test engineer - Developers
PMO/Project Support- Miranda